MERIDIAN ADVISORY GROUP

DIGITAL & TECHNOLOGY TRANSFORMATION

JOB CARD DOCUMENT

Phoenix — Enterprise CRM Modernisation Programme

TechNova Corporation · Digital Transformation

MAG-JC-2026-0047  ·  v3.1  ·  APPROVED  ·  CONFIDENTIAL

Programme Manager: Nathaniel Ashford

Executive Sponsor: Dr. Priya Ramasamy (TechNova VP Operations)

Issued: 22 April 2026

01  Document Control & Version History

Ownership, distribution, and change history

Document Owner: Nathaniel Ashford   |   Approver: Dr. Priya Ramasamy   |   Classification: CONFIDENTIAL

## Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| v1.0 | 15 January 2026 | Nathaniel Ashford | Initial draft — Initiation phase |
| v2.0 | 28 February 2026 | Saoirse Gallagher | Design phase complete; scope, RACI, and SDD references added |
| v3.0 | 31 March 2026 | Nathaniel Ashford | Sprint 1–3 complete; risk register updated; issues I-001, I-003 resolved |
| v3.1 | 22 April 2026 | Linh Tran | Sprint 4 in-progress; Issue I-002 raised; defect summary updated; QC items updated |

## Distribution List

| Name | Role | Organisation | Copy Type |
| --- | --- | --- | --- |
| Dr. Priya Ramasamy | Executive Sponsor | TechNova Corporation | Controlled |
| Nathaniel Ashford | Programme Manager | Meridian Advisory Group | Controlled |
| Dr. Priya Ramasamy | Executive Sponsor | TechNova Corporation | Information |
| Brendan Mwangi | Technology Owner | TechNova Corporation | Information |
| Candice Ofoegbu | Business Process Owner | TechNova Corporation | Information |
| James Kowalski | Compliance Authority | TechNova Corporation | Information |

02  Executive Summary

Programme overview, current health, and recommendation

🟢  PROGRAMME STATUS: GREEN — On Track

TechNova Corporation is executing a USD 4.8M, 9-month programme to replace its legacy Siebel CRM with Salesforce Sales Cloud, Service Cloud, and a bespoke Analytics Hub, decommissioning 14 satellite systems and consolidating 3.2M customer records.

| Metric | Value |
| --- | --- |
| Total Budget | $4,800,000 |
| Consumed to Date | $2,116,000 (44.1%) |
| Remaining | $2,684,000 |
| Billing Type | Time & Materials (T&M) with Fixed-Fee Milestones |

## Strategic Alignment

- FY26 Digital Transformation Strategy — Pillar 2: Customer 360

- Board mandate to reduce operational cost by 18% over 3 years

- Regulatory compliance — CCPA, GDPR data residency requirements

- Net Promoter Score (NPS) improvement target from 42 to 68 by Q4 FY27

## Key Risks

- ⚠ Data quality issues in legacy Siebel — 340K orphaned records identified

- ⚠ Third-party middleware vendor (IntelliConnect) resource constraint in Sprint 5

## Recommendation

Proceed to Sprint 5 (Integration & Data Migration). Initiate Parallel Run protocol by 2026-07-01. Board sign-off on Acceptance Criteria v2.3 required by 2026-05-15.

03  Job Overview

Engagement details, budget, and team composition

## Engagement Details

| Field | Value | Field | Value |
| --- | --- | --- | --- |
| Project Name | Phoenix — Enterprise CRM Modernisation Programme | Project Code | PHX-2026 |
| Client | TechNova Corporation | Engagement Ref | MAG-ENG-2026-0047 |
| Project Type | Digital Transformation | Methodology | Hybrid Agile-Waterfall |
| Start Date | 06 January 2026 | End Date | 30 September 2026 |
| Billing Type | Time & Materials (T&M) with Fixed-Fee Milestones | Currency | USD |
| Programme Manager | Nathaniel Ashford | Delivery Lead | Saoirse Gallagher |
| Solution Architect | Yusuf Okonkwo | QA Lead | Linh Tran |
| Change Manager | Marcus Delacroix | Sponsor | Dr. Priya Ramasamy (TechNova VP Operations) |

04  Scope

In-scope, out-of-scope, assumptions, constraints, and exclusions

## In-Scope

- Migration of 3.2M customer records from Siebel CRM 8.1 to Salesforce Sales Cloud

- Salesforce Service Cloud implementation — Case Management, Knowledge Base, Live Chat

- Custom Analytics Hub (React + Power BI Embedded) replacing 4 legacy BI tools

- API gateway layer (MuleSoft Anypoint) integrating 6 downstream systems

- Single Sign-On (SSO) via Azure AD B2C for 1,200 internal users and 480 partners

- Data Quality Remediation — deduplication and enrichment of customer master data

- User training for 1,200 internal users across 8 business units

- Hypercare support — 90-day post-go-live monitoring and L1/L2 ticket handling

- Decommission of 14 legacy satellite CRM systems

- UAT coordination with 3 external partner organisations

## Out-of-Scope

- 🚫 ERP integration (SAP S/4HANA) — covered under separate programme PHX-ERP-2026

- 🚫 Legacy billing system replacement — deferred to FY27 roadmap

- 🚫 Mobile application development — separate workstream governed by IT PMO

- 🚫 Third-party vendor contract renegotiation

- 🚫 Hardware procurement or data centre reconfiguration

## Assumptions

| # | Assumption |
| --- | --- |
| A01 | Client IT team will provide dedicated DBA resource (2 FTE) for data migration windows |
| A02 | Salesforce licences (1,200 Sales Cloud, 800 Service Cloud) procured by 2026-03-01 |
| A03 | Azure AD B2C tenant provisioned and configured by client IT by 2026-04-15 |
| A04 | All source system API documentation current and accessible by 2026-02-01 |
| A05 | Business SMEs available minimum 40% of sprint capacity for UAT and sign-off |

## Constraints

| # | Constraint |
| --- | --- |
| C01 | Go-live window restricted to 2026-09-27–2026-09-28 (regulatory freeze avoidance) |
| C02 | MuleSoft environment must remain on-premises due to data sovereignty requirements |
| C03 | No production environment access for consultants — all deployments via client DevOps |
| C04 | SOX compliance — all financial data fields require dual approval workflow |

## Exclusions

- Meridian Advisory Group will not provide permanent technical operations staff

- Consultant firm does not assume liability for pre-existing data quality defects

05  Stakeholder Matrix

Full stakeholder register with influence, interest, and engagement strategy

| Name | Title | Organisation | Role | Influence | Interest | Engagement | Comms |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dr. Priya Ramasamy | VP Operations | TechNova Corporation | Executive Sponsor | High | High | Champion | Bi-weekly Steering |
| Brendan Mwangi | Chief Information Officer | TechNova Corporation | Technology Owner | High | Medium | Supportive | Monthly + Ad Hoc |
| Candice Ofoegbu | Head of Sales Operations | TechNova Corporation | Business Process Owner | High | High | Champion | Weekly Sprint Reviews |
| James Kowalski | Group Compliance Officer | TechNova Corporation | Compliance Authority | High | Medium | Neutral | Monthly Compliance Gate |
| Nathaniel Ashford | Senior Manager | Meridian Advisory Group | Programme Manager (Consultant) | Medium | High | Lead | Daily Stand-up |
| IntelliConnect PM | Project Manager | IntelliConnect Ltd | Third-Party Middleware Vendor | Medium | Low | Monitor | Weekly Technical Call |

06  RACI Matrix

R=Responsible · A=Accountable · C=Consulted · I=Informed

| Activity | Exec Sponsor | PMO | Dev Lead | Arch Lead | QA Lead | Change Mgr | Client IT | Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Governance & Steering | A | R | C | C | I | I | I | I |
| Sprint Planning & Backlog Refinement | I | R | C | C | I | C | I | I |
| Salesforce Configuration & Build | I | I | R | C | C | I | C | I |
| MuleSoft API Development | I | I | C | R | I | I | A | I |
| Data Migration Execution | I | A | C | C | R | I | R | I |
| UAT Coordination & Sign-off | A | I | I | I | I | R | I | C |
| Security & Compliance Review | I | I | I | C | I | I | C | R |
| Go-Live Authorisation | R | C | I | I | I | C | C | C |
| Hypercare Monitoring | I | A | R | C | I | C | R | I |
| Decommission of Legacy Systems | A | C | I | I | C | I | R | I |

07  Workflow & Process Flow

End-to-end programme workflow with phase gates and decision points

Process flow diagram is embedded in the HTML and PDF versions. ASCII representation:

INITIATION → DISCOVERY → DESIGN → BUILD (6 Sprints) → TEST → DEPLOY → HYPERCARE

## Workflow Steps

| # | Phase | Activity | Owner | Duration | Gate |
| --- | --- | --- | --- | --- | --- |
| 1 | Initiation | Engagement Kick-off | Programme Manager | 1 week | Steering Committee Approval |
| 2 | Discovery | Current-State Assessment & Gap Analysis | Solution Architect | 3 weeks | Business Sign-off on Gap Analysis |
| 3 | Design | Solution Architecture & Design | Solution Architect + Dev Lead | 4 weeks | Architecture Review Board Approval |
| 4 | Build | Iterative Development (6 × 2-week Sprints) | Delivery Lead | 12 weeks | Sprint Review Acceptance per Iteration |
| 5 | Test | System Integration Testing & UAT | QA Lead + Business SMEs | 5 weeks | UAT Sign-off with <5 Critical Defects Outstanding |
| 6 | Deploy | Go-Live & Cutover | Programme Manager + Client IT | 3 days | Exec Sponsor Go-Live Authorisation |
| 7 | Hypercare | Post-Go-Live Support (90 days) | Delivery Lead + QA Lead | 90 days | Formal Acceptance Criteria Met — Client Sign-off |

## Inputs & Outputs per Step

| Step | Inputs | Outputs | Tools |
| --- | --- | --- | --- |
| 1. Initiation | Signed SOW, Project Charter | Kick-off Deck, RAID Log v1, Comms Plan | Confluence, JIRA, Miro |
| 2. Discovery | Legacy System Documentation, SME Interviews | As-Is Process Maps, Gap Analysis Report, Data Profile | Miro, Lucidchart, Excel |
| 3. Design | Gap Analysis, Salesforce Best Practices, MuleSoft Patterns | Solution Design Document, API Specification, Data Dictionary | Salesforce DevOps Center, MuleSoft Design Center, Draw.io |
| 4. Build | Approved Design Documents, Sprint Backlog | Configured Salesforce Orgs, API Endpoints, Analytics Dashboard | JIRA, GitHub, Salesforce Sandbox, MuleSoft CloudHub |
| 5. Test | Test Strategy, Test Cases, Configured System | Test Completion Report, Defect Log, UAT Sign-off | Jira Zephyr, Postman, Selenium, Excel |
| 6. Deploy | Go-Live Readiness Report, Cutover Runbook, Rollback Plan | Live Production System, Cutover Report | Salesforce Production Org, MuleSoft Production, Runbook |
| 7. Hypercare | Incident Reports, User Feedback, Monitoring Dashboards | Weekly Health Reports, Defect Fixes, Knowledge Transfer Docs | Salesforce Service Cloud, PagerDuty, Confluence |

08  Screenshots & Artefacts

Application screens captured via wkhtmltoimage

Screenshots are generated and saved to the /screenshots/ directory. See the HTML/PDF output for embedded visual artefacts.

| Fig. | Caption | Filename |
| --- | --- | --- |
| Fig 1 | Salesforce Sales Cloud — Accounts View | screenshots/01-salesforce-accounts.png |
| Fig 2 | Analytics Hub — Executive KPI Dashboard | screenshots/02-analytics-hub.png |
| Fig 3 | MuleSoft Anypoint — API Management Console | screenshots/03-mulesoft-console.png |
| Fig 4 | JIRA Board — Sprint 4 Kanban | screenshots/04-jira-board.png |
| Fig 5 | Salesforce Service Cloud — Case Management | screenshots/05-service-cloud.png |
| Fig 6 | Data Migration — Reconciliation Dashboard | screenshots/06-migration-dashboard.png |

09  Standard Operating Procedures

Documented step-by-step operational protocols

## SOP-001 — Weekly Sprint Ceremony Protocol

Purpose: Ensure consistent sprint cadence and stakeholder visibility

- 1. Monday 09:00: Sprint Planning — Dev Lead runs backlog refinement, selects committed stories

- 2. Daily 09:15: Stand-up — Each team member reports: Done / Doing / Blocked (15 min max)

- 3. Wednesday 14:00: Mid-sprint check — PM reviews burn-down, escalates blockers

- 4. Friday 15:00: Sprint Review — Demo to business stakeholders; collect acceptance

- 5. Friday 16:00: Retrospective — Team reviews process; action items logged in Confluence

- 6. PM updates RAID Log, Risk Register, and Status Report before Monday 08:00

## SOP-002 — Change Request Management

Purpose: Control scope changes through a governed approval process

- 1. Requester submits Change Request (CR) via Jira using CR template (min 72 hrs before sprint start)

- 2. PM assesses impact on scope, timeline, and budget within 48 hours

- 3. CR categorised: Minor (<1 day effort) — PM approval only; Major (>1 day) — Change Board required

- 4. Change Board meets bi-weekly; quorum: Exec Sponsor + CIO + PM

- 5. Approved CRs added to next sprint backlog; rejected CRs logged with rationale

- 6. PM updates Project Charter and SOW amendment if budget impact >$25,000

## SOP-003 — Defect Management & Escalation

Purpose: Ensure defects are triaged, tracked, and resolved within agreed SLAs

- 1. Tester logs defect in Jira with severity (P1/P2/P3/P4), description, steps to reproduce, and evidence

- 2. QA Lead triages within 4 hours; assigns to owner and sets target fix date

- 3. P1 (Critical): Fix within 24 hours; automatic escalation to PM and Exec Sponsor

- 4. P2 (Major): Fix within 3 business days; weekly review in Sprint standup

- 5. P3/P4: Scheduled into subsequent sprint; closure requires QA Lead re-test

- 6. Defect closure logged in Test Completion Report; pattern analysis done at Sprint Retro

10  Inputs

Data, system, and human inputs required for programme execution

| ID | Type | Source | Description | Format | Frequency |
| --- | --- | --- | --- | --- | --- |
| IN-001 | System | Siebel CRM 8.1 | Full customer master data export (CSV/XML) | CSV + XML | One-time migration |
| IN-002 | System | SAP ERP (read-only) | Customer purchase history and contract data | REST API | Real-time sync post go-live |
| IN-003 | Document | Legal / Compliance | Data retention policies and consent flags | Excel + PDF | One-time input + quarterly updates |
| IN-004 | Human | Business SMEs | Process validation, UAT test execution, sign-off | Confluence, Jira | Per sprint (2-week cycles) |
| IN-005 | System | Azure AD B2C | User identity and role provisioning for SSO | SAML 2.0 / OAuth 2.0 | Real-time on login |

11  Outputs & Deliverables

Programme deliverables, system outputs, and SLAs

| ID | Type | Destination | Description | Format | SLA |
| --- | --- | --- | --- | --- | --- |
| OUT-001 | System | Salesforce Sales Cloud | Migrated and enriched customer master | Salesforce Records | 99.5% record accuracy post-migration |
| OUT-002 | Document | Client IT + PMO | Weekly Status Report (RAG) | PDF + Confluence | Every Friday by 17:00 EST |
| OUT-003 | System | Analytics Hub | Real-time KPI dashboards via Power BI Embedded | REST API JSON | < 3 seconds dashboard load time |
| OUT-004 | Document | Steering Committee | Monthly Executive Summary (Steering Pack) | PowerPoint + PDF | 5 business days before Steering meeting |
| OUT-005 | Document | Compliance / Audit | Data Migration Audit Trail and Reconciliation Report | PDF + Excel | Within 10 business days post-migration |

12  Tools & Technology Stack

Full technology inventory, versions, and licence ownership

| Category | Tool / Platform | Version | Purpose | Licences | Owner |
| --- | --- | --- | --- | --- | --- |
| CRM Platform | Salesforce Sales Cloud + Service Cloud | Winter '26 | Core CRM replacement | 1,200 Sales + 800 Service | TechNova IT |
| Integration | MuleSoft Anypoint Platform | 4.6.x | API gateway and middleware orchestration | Platinum On-Premises | TechNova IT |
| Project Management | Jira Software | 9.4 Cloud | Sprint management, defect tracking | Enterprise (unlimited) | Meridian AG |
| Documentation | Confluence | 7.19 Cloud | Knowledge base, runbooks, SOP library | Enterprise (unlimited) | Meridian AG |
| Analytics | Power BI Embedded (A4 SKU) | 2026-03 | Embedded analytics in custom React portal | A4 Capacity (per-node) | TechNova IT |
| DevOps | GitHub + GitHub Actions | Enterprise Cloud | Source control, CI/CD pipelines | Enterprise (300 seats) | TechNova IT |
| Testing | Jira Zephyr Scale | 9.x | Test case management, execution tracking | Commercial (150 seats) | Meridian AG |
| Identity | Azure Active Directory B2C | P2 tier | SSO and MFA for all users | P2 per-user (1,680) | TechNova IT |
| Monitoring | Datadog APM + Log Management | Enterprise | Post-go-live performance and error monitoring | Annual enterprise contract | TechNova IT |
| Collaboration | Microsoft Teams + Miro | M365 E5 + Miro Business | Remote collaboration, workshop facilitation | M365 E5 (bundled) | Shared |

13  Responsibilities

Role-based responsibility breakdown

## Programme Manager (Meridian) — Nathaniel Ashford

- Overall programme delivery, governance, and stakeholder management

- Weekly status reporting and Steering Committee facilitation

- RAID Log ownership and risk escalation

- Budget tracking and forecasting (monthly ±5% variance reporting)

- Change Request assessment and Change Board coordination

- Final quality gate approval before each phase transition

## Solution Architect (Meridian) — Yusuf Okonkwo

- End-to-end technical design authority — Salesforce, MuleSoft, Analytics Hub

- Architecture Review Board preparation and presentation

- Vendor technical liaison (Salesforce AE, MuleSoft CSM, IntelliConnect PM)

- Data model governance and API contract management

- Security architecture and SOX compliance technical review

## Delivery Lead (Meridian) — Saoirse Gallagher

- Sprint planning, backlog management, and velocity tracking

- Day-to-day team coordination across 6 development squads

- Jira configuration, board health, and burn-down reporting

- Escalation point for development and integration blockers

- Hypercare lead during 90-day post-go-live period

## QA Lead (Meridian) — Linh Tran

- Test strategy, test plan, and test case design across all workstreams

- UAT coordination with business SMEs and partner organisations

- Defect triage, SLA management, and trend analysis

- Test completion report authorship and sign-off facilitation

- Regression suite maintenance and automation framework ownership

## Change Manager (Meridian) — Marcus Delacroix

- Organisational change management strategy and impact assessment

- Training needs analysis and delivery plan for 1,200 users

- Stakeholder engagement plan execution and sentiment tracking

- Communication plan management and content review

- Benefits realisation framework and post-go-live adoption monitoring

14  Timeline & Milestones

Programme phases with status and milestone register

See the HTML/PDF version for the full Gantt chart visualization.

| Phase | Start | End | Milestone | Status |
| --- | --- | --- | --- | --- |
| Discovery & Analysis | 06 January 2026 | 30 January 2026 | Gap Analysis Approved | Complete |
| Solution Design | 27 January 2026 | 27 February 2026 | Architecture Sign-off | Complete |
| Sprint 1 — Core CRM Config | 02 March 2026 | 13 March 2026 | Sales Cloud MVP | Complete |
| Sprint 2 — Service Cloud | 16 March 2026 | 27 March 2026 | Service Cloud MVP | Complete |
| Sprint 3 — API Layer | 30 March 2026 | 10 April 2026 | API Gateway Live | Complete |
| Sprint 4 — Data Migration Dry Run | 13 April 2026 | 24 April 2026 | DM Reconciliation Report | In Progress |
| Sprint 5 — Analytics Hub | 27 April 2026 | 08 May 2026 | Analytics Dashboard Demo | Planned |
| Sprint 6 — UAT & Hardening | 11 May 2026 | 05 June 2026 | UAT Sign-off | Planned |
| Go-Live Preparation & Cutover | 14 September 2026 | 28 September 2026 | Production Go-Live | Planned |
| Hypercare (90 days) | 29 September 2026 | 28 December 2026 | Formal Acceptance | Planned |

15  Risk Register

Programme risks with probability, impact, mitigation, and ownership

| ID | Category | Description | Prob. | Impact | Rating | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Data | 340K orphaned customer records in Siebel with no owner mapping — risk of data loss or duplication post-migration | High | High | Critical | Yusuf Okonkwo | Open |
| R-002 | Resource | IntelliConnect vendor has indicated potential 3-week resource constraint starting Sprint 5; API completion may slip | Medium | High | High | Nathaniel Ashford | Escalated |
| R-003 | Technical | MuleSoft on-premises version 4.6.x known bug (MULE-19482) affecting large payload routing — patch not yet GA | Medium | Medium | Medium | Yusuf Okonkwo | Mitigated |
| R-004 | Scope | Sales Operations requesting addition of CPQ module — not in original SOW; potential scope creep | High | Medium | High | Nathaniel Ashford | Open |
| R-005 | Compliance | GDPR right-to-erasure requests during migration window could corrupt migration state if not handled | Low | High | Medium | Marcus Delacroix | Mitigated |

16  Issue Log

Active and resolved issues with impact and resolution

| ID | Description | Impact | Raised | Owner | Status | Resolution |
| --- | --- | --- | --- | --- | --- | --- |
| I-001 | Azure AD B2C tenant provisioning delayed 2 weeks due to TechNova IT internal change freeze | Sprint 3 SSO integration pushed by 8 days | 10 March 2026 | Brendan Mwangi (TechNova CIO) | Resolved | Emergency CAB approval secured; tenant provisioned ahead of revised schedule |
| I-002 | Salesforce API Governor Limits hit during bulk migration dry run — 5,000 records/batch exceeded | Dry run aborted; migration script requires re-architecture | 15 April 2026 | Yusuf Okonkwo | In Progress | Bulk API v2 chunking strategy being implemented; ETA 2026-04-25 |
| I-003 | Business SME availability below 40% commitment in Sprint 3; 6 user stories returned without acceptance | 6 stories deferred to Sprint 4 backlog; velocity reduced 22% | 27 March 2026 | Candice Ofoegbu | Resolved | Formal escalation to Dr. Ramasamy; dedicated SME calendar blocks enforced from Sprint 4 |

17  Quality Checklist

QA gate items, compliance checks, and training readiness

| Category | Quality Item | Required | Status |
| --- | --- | --- | --- |
| Documentation | Project Charter approved by Exec Sponsor | YES | Done |
| Documentation | Solution Design Document signed off by Architecture Review Board | YES | Done |
| Documentation | Data Dictionary v2.0 reviewed and approved | YES | Done |
| Documentation | Test Strategy reviewed by QA Lead and Client | YES | Done |
| Documentation | Go-Live Runbook and Rollback Plan approved | YES | Pending |
| Technical | All Salesforce configuration peer-reviewed before deployment to UAT | YES | Done |
| Technical | API contracts validated against OpenAPI 3.0 specification | YES | Done |
| Technical | Security penetration test completed and findings remediated (P1/P2) | YES | In Progress |
| Technical | Performance test: 1,000 concurrent users at <2s response time | YES | Pending |
| Technical | Data migration reconciliation: >99.5% record count and field accuracy | YES | Pending |
| Compliance | GDPR Data Protection Impact Assessment (DPIA) completed | YES | Done |
| Compliance | SOX dual-approval workflow verified for all financial data flows | YES | In Progress |
| Compliance | Accessibility audit (WCAG 2.1 AA) on Analytics Hub | Optional | Pending |
| Training | Training materials reviewed and approved by business leads | YES | In Progress |
| Training | Train-the-trainer sessions completed for 8 super-user champions | YES | Pending |

18  Testing Summary

Test strategy, types, coverage, and defect summary

Risk-based testing approach aligned to ISO 29119. Coverage tiers: Unit (dev-owned), Integration, System, Regression, UAT, Performance, Security, and Accessibility.

## Defect Summary

| Priority | Count | Status |
| --- | --- | --- |
| P1 Critical | 3 | ⚠ Attention Required |
| P2 Major | 14 | ⚠ Monitor |
| P3 Minor | 42 | Scheduled |
| P4 Trivial | 30 | Backlog |
| Total: 89 | 71 Closed | 18 Open |

## Test Types & Coverage

| Test Type | Owner | Tool | Coverage | Status |
| --- | --- | --- | --- | --- |
| Unit Testing | Development Team | Jest / Apex Tests | 85% code coverage minimum | In Progress |
| System Integration Testing | QA Lead | Postman + Jira Zephyr | All 47 API endpoints; 218 test cases | In Progress |
| User Acceptance Testing | Business SMEs + QA Lead | Jira Zephyr + Excel | 127 business scenarios; 3 business units | Planned |
| Regression Testing | QA Lead | Selenium WebDriver + GitHub Actions | Full smoke pack after every deployment | Planned |
| Performance Testing | QA Lead | Apache JMeter | 1,000 concurrent users, 4-hour soak test | Planned |
| Security Penetration Testing | TechNova InfoSec (external vendor) | Burp Suite Pro, OWASP ZAP | OWASP Top 10, SANS 25 | In Progress |
| Data Migration Testing | QA Lead + Client DBA | Custom Python reconciliation scripts | 100% record count; 99.5% field accuracy | Planned |

19  Acceptance Criteria

Formal acceptance criteria — must be met for programme sign-off

| ID | Deliverable | Acceptance Criterion | Verified By | Status |
| --- | --- | --- | --- | --- |
| AC-001 | Salesforce CRM Configuration | All 127 UAT scenarios pass with zero P1 defects outstanding | QA Lead + Business SMEs | Pending |
| AC-002 | Data Migration | ≥99.5% record count accuracy; ≥99.0% field-level accuracy; zero critical data losses | Client DBA + QA Lead | Pending |
| AC-003 | MuleSoft API Layer | All 47 API endpoints return correct responses per OpenAPI spec; <200ms p95 latency under 500 RPS | Solution Architect | In Progress |
| AC-004 | Analytics Hub | All 12 dashboards load in <3 seconds; data refreshes within 5-minute SLA; WCAG 2.1 AA compliant | QA Lead + TechNova Analytics Team | Pending |
| AC-005 | SSO & Access Management | All 1,680 users able to authenticate within 3 seconds; MFA enforced for all admin roles | TechNova IT Security | In Progress |
| AC-006 | Training & Readiness | ≥80% of users score ≥75% on post-training assessment; all super-user champions certified | Change Manager | Pending |
| AC-007 | Legacy Decommission | 14 legacy systems formally decommissioned; no active data writes to legacy after Go-Live+7 | TechNova CIO | Pending |
| AC-008 | Overall Programme | Budget variance ≤10%; schedule variance ≤15 days; formal acceptance signed by Exec Sponsor | Executive Sponsor | Pending |

20  Communication Plan

Stakeholder communication frequency, format, and channel matrix

| Audience | Format | Frequency | Owner | Channel | Distribution |
| --- | --- | --- | --- | --- | --- |
| Executive Steering Committee | Steering Pack (PPT + PDF) | Bi-monthly | PM | In-person / Video | Dr. Ramasamy, Brendan Mwangi, TechNova Board Rep |
| Programme Core Team | Weekly Status Report (PDF) | Weekly (Friday) | PM | Email + Confluence | Full core team + PMO |
| Sprint Team | Daily Stand-up (15 min) | Daily | Delivery Lead | MS Teams | All squad leads |
| Business Stakeholders | Sprint Review Demo | Bi-weekly | Delivery Lead | Video + Jira | Business SMEs, Sales Ops, Service Ops |
| End Users | Change Newsletter | Monthly | Change Manager | Email + Intranet | All 1,200 TechNova staff affected |
| External Vendors | Technical Workgroup Call | Weekly | Solution Architect | MS Teams | IntelliConnect PM, Salesforce CSM, MuleSoft CSM |
| Compliance / Audit | Compliance Gate Report | Monthly | PM + Change Mgr | Formal email + SharePoint | James Kowalski (Compliance), External Auditor |

21  Handover Notes

Knowledge transfer, operational readiness, and open items

## Knowledge Transfer Activities

- 12 Confluence spaces established with full runbooks, SOPs, and operational guides

- 4-week embedded handover period with TechNova IT team starting 2026-09-29

- Shadow sessions completed: Salesforce Admin (x3), MuleSoft Ops (x2), Analytics (x2)

- All custom code repositories transferred to TechNova GitHub Enterprise organisation

- Salesforce admin credentials transferred via approved secrets management process

## Operational Readiness

- TechNova Salesforce Admin team (3 FTE) trained and certified (ADM 201)

- MuleSoft operations runbook approved by TechNova IT Lead

- Datadog monitoring dashboards and PagerDuty alerting configured for TechNova on-call

- L1/L2 support desk scripts and escalation paths documented in Service Cloud Knowledge Base

- Monthly performance review cadence established (first: 2026-10-28)

## Open Items at Handover

- ⚠ CPQ module scope decision pending Change Board (CR-2026-014) — 2026-04-29

- ⚠ Power BI Embedded licence renewal due 2026-09-30 — TechNova procurement to action

- ⚠ WCAG 2.1 AA remediation on Analytics Hub charts — estimated 3 dev-days

- ⚠ Salesforce Summer '26 upgrade compatibility review required by 2026-07-15

22  Approval Sign-off

All signatures required before Go-Live authorisation

All approvers below must sign this document before the programme can proceed to Go-Live. Target date: 15 May 2026.

| Role | Name | Organisation | Signature | Date | Status |
| --- | --- | --- | --- | --- | --- |
| Executive Sponsor | Dr. Priya Ramasamy | TechNova Corporation | _________________________ | ___________ | Pending |
| Chief Information Officer | Brendan Mwangi | TechNova Corporation | _________________________ | ___________ | Pending |
| Programme Manager | Nathaniel Ashford | Meridian Advisory Group | _________________________ | ___________ | Pending |
| Engagement Partner | Victoria Osei-Mensah | Meridian Advisory Group | _________________________ | ___________ | Pending |
| Compliance Officer | James Kowalski | TechNova Corporation | _________________________ | ___________ | Pending |

A  Appendix A — Glossary

Definitions of key terms and acronyms

| Term | Definition |
| --- | --- |
| API | Application Programming Interface — a set of protocols enabling software communication |
| CRM | Customer Relationship Management — software managing company interactions with customers |
| DPIA | Data Protection Impact Assessment — GDPR-mandated analysis of privacy risks |
| RAID | Risks, Assumptions, Issues, Dependencies — standard programme management log |
| RACI | Responsible, Accountable, Consulted, Informed — responsibility assignment matrix |
| SOX | Sarbanes-Oxley Act — US federal law governing financial data controls |
| SOP | Standard Operating Procedure — documented step-by-step process instruction |
| SSO | Single Sign-On — authentication allowing one login to access multiple systems |
| T&M | Time & Materials — billing model where client pays for actual hours and costs |
| UAT | User Acceptance Testing — end-user validation of system against business requirements |
| WCAG | Web Content Accessibility Guidelines — international accessibility standard |

B  Appendix B — References

Source documents cited in this job card

| Reference | Description | Date |
| --- | --- | --- |
| SOW-2026-0047 | Statement of Work — Phoenix CRM Modernisation | 05 January 2026 |
| PHX-SDD-v2.1 | Solution Design Document v2.1 | 27 February 2026 |
| PHX-TS-v1.3 | Test Strategy Document v1.3 | 15 March 2026 |
| PHX-DM-PLAN-v1.0 | Data Migration Plan v1.0 | 28 March 2026 |
| PHX-DPIA-2026 | GDPR Data Protection Impact Assessment | 10 February 2026 |
| PHX-SEC-RPT-001 | Penetration Test Interim Report | 10 April 2026 |